## Multi-Currency Implementation G
ID | Task Name | Duration | Start Day | End Day | Dependencies
1 | Backend (BE) Workstream | 22 Days | Day 1 | Day 22
1.1 | DB Migration & Wallet Entity Constraints | 3 Days | Day 1 | Day 3 | None
1.2 | Treasury/Master Wallet Initialization (INR/BDT) | 3 Days | Day 4 | Day 6 | 1.1
1.3 | FX Engine & ExchangeRate Service | 4 Days | Day 7 | Day 10 | 1.2
1.4 | Atomic Bridge Orchestration (5-Legged Logic) | 8 Days | Day 11 | Day 18 | 1.3
1.5 | Commission Routing & Revenue Logic | 4 Days | Day 19 | Day 22 | 1.4
2 | Frontend (FE) Workstream | 8 Days | Day 7 | Day 14
2.1 | Multi-Wallet Creation Workflow (Subscriber Opt-in) | 3 Days | Day 7 | Day 9 | 1.1
2.2 | Transfer Initiation UI (Currency Selector/Rate Preview) | 5 Days | Day 10 | Day 14 | 2.1, 1.3
3 | Dashboard & Analytics | 10 Days | Day 15 | Day 24
3.1 | Multi-Currency Balance Cards (Dashboard Update) | 5 Days | Day 15 | Day 19 | 1.2
3.2 | Treasury Liquidity Monitoring & Alerting | 5 Days | Day 20 | Day 24 | 3.1
4 | Reporting (Jasper) | 10 Days | Day 23 | Day 32
4.1 | Money Flow Report Redesign (FXBlock integration) | 6 Days | Day 23 | Day 28 | 1.1, 1.4
4.2 | Audit Alignment & Historical Data Verification | 4 Days | Day 29 | Day 32 | 4.1
5 | QA, Testing & Feedback | 18 Days | Day 33 | Day 50
5.1 | System Integration Testing (SIT) - End-to-End FX | 8 Days | Day 33 | Day 40 | All BE/FE/UI
5.2 | User Acceptance Testing (UAT) & Fixes | 6 Days | Day 41 | Day 46 | 5.1
5.3 | Final Financial Reconciliation & Deployment Prep | 4 Days | Day 47 | Day 50 | 5.2